UAE Integrity Benchmarking Study — Executive Brief

Integrity Section · Internal Audit and Risk Management Sector · Department of Government Enablement — Abu Dhabi

4 September 2026 · DRAFT for review · Distilled from the full 26-section study; every claim traces to the evidence registers (all sources accessed 4 September 2026, search-verified official content pending one-click URL confirmation).

1. The Answer

Where we stand. The Integrity Section scores a provisional 57 of 100 on the study model — investigations, fraud risk assessment (312 risks · 497 control owners · 8 registers · 41 entities) and executive reporting at Advanced level; whistleblowing channel, case management, conflict of interest, and gifts machinery at Developing or below. The maturity is embodied in practice, not yet institutionalised in charter, systems and staffing. (Current-state register: carried from the project record.)

What the leaders do differently. They place the reporting channel outside the organization or under certification, with anonymity and two-way dialogue; they separate investigation from decision structurally; they publish outcomes and metrics; and government bodies anchor reporter protection in a legal instrument, not a webpage promise.

The decision requested. Approve the three Critical actions (charter and investigation mandate; channel capability upgrade; violations committee separated from investigation) to start Q4 2026 — cost is chiefly internal effort plus one hosted-channel procurement; the risk carried by inaction is reporter bypass and key-person dependency.

2. Top 5 UAE Benchmark Entities (scored /100, assessed in session from disclosed evidence)

| Entity | Score | What it evidences | What we take from it |
| --- | --- | --- | --- |
| Mubadala | 67 | Only UAE entity with ISO 37001 + 37301 + 37002 together; Ethics & Compliance Office that itself investigates | Certification path; chartered office owning ethics, channel and investigations |
| DFSA (DIFC) | 65 | Enforcement with Decision Making Committee having "no previous direct involvement in establishing the evidence"; tribunal appeal; published notices; 2025 whistleblowing thematic review | Structural separation of investigation from decision; supervision by data |
| ADGM | 63 | Whistleblower Protection Regulations 2024 (in force 5 July 2024): protected disclosures, anonymity, protection from "any form of detriment", 6-year records, sanctions | Ready checklist for a departmental whistleblowing policy |
| Dubai Financial Audit Authority | 63 | Nazaha public reporting; Decision 2/2025 statutory employment protection for reporters; anti-fraud framework; Al Mo’ashir dashboards; own violations committee | Closest public-sector operating model end to end |
| ADNOC | 59 | Takallam channel: independent operator (SpeakUp, Amsterdam), anonymous two-way dialogue, web/app/phone, multilingual, open to the public; code editions since 2016 | The channel attribute set Tahadath should reach |

Dimension-specific references: Etihad (Report-Key case tracking; annual COI declaration cycle), Emirates NBD (published whistleblowing metrics; named Head of Fraud Prevention and Investigation), FAB (named vendor, unique case numbers, WhatsApp channel).

3. Federal and Dubai Reference Entities

| Entity | Evidenced practice | Relevance to DGE |
| --- | --- | --- |
| Ministry of Finance | "Trust Voice" whistleblowing service + MOFUAE app channel: secure, confidential, open to all stakeholders including the public, anti-retaliation stated; lineage from the 2018 federal anti-fraud guidance. Covers MoF itself — the cross-government platform is Wajib. | Federal ministry precedent for a department-owned named channel with public scope |
| Federal Authority for Government Human Resources (FAHR) | Federal Code of Professional Conduct and Ethics (Cabinet Resolution 79/2023 under Decree-Law 49/2022): COI avoidance with family scope to the 4th degree and right to request transfer; gifts barred except symbolic items, with a designated unit to receive gifts; duty to report irregularities; committee-based discipline. | The normative base for our COI cycle, gifts register and conduct attestation |
| Central Bank of the UAE | Own encrypted whistleblowing portal (2021): anonymity by skipping identification, evidence upload, public eligibility; enforcement chain (Examination vs Enforcement) with individual accountability (AED 200m institutional + AED 500,000 personal sanction with prohibition). | Encrypted in-house channel design; separation of examination from sanction |
| DFSA — DIFC | First UAE regulatory whistleblowing regime (7 April 2022) binding all regulated entities: written procedures to report, assess, escalate; identity protection; thematic review data (97% anonymity measures; 88% training; only 39% open channels to third parties; weak post-report treatment monitoring). | Regime design plus the only sector-wide dataset; post-report monitoring is the gap we can close first |
| ADGM (Abu Dhabi) | Whistleblower Protection Regulations 2024 + AMANAH channel; FSRA enforcement with published penalties and settlement discounts (Aarna Capital USD 504,000). | Abu Dhabi’s own statutory benchmark; policy checklist and sanction logic |
| UAE Accountability Authority | Federal Decree-Law 56/2023; administrative investigations into misappropriation, COI, abuse of authority; prosecution referral gateway; Wajib platform adopted across all ministries and federal entities (2023); confidentiality without mandatory identity disclosure; leniency for self-reporting participants. | The referral environment our cases feed; leniency and confidentiality design |

4. Main Gaps and Risks (from the gap analysis)

| Gap | Risk if unaddressed | Action | Priority |
| --- | --- | --- | --- |
| Channel: no anonymity, tracking, two-way, independent hosting evidenced on Tahadath | Reporters bypass to Wajib or stay silent; late detection | Upgrade Tahadath or procure hosted channel | Critical |
| Investigation method not institutionalised (no charter/manual in record) | Key-person loss removes capability; process challengeable | Charter + manual + violations-committee protocol | Critical |
| Manual case management; no SLA, audit trail, trend view | Cannot evidence control of caseload to oversight | Case system encoding existing discipline | High |
| COI per-case only; no annual declaration cycle | Undeclared conflicts surface after damage — as own casework shows | Annual cycle + procurement COI gate | High |
| Gifts register not evidenced; analytics case-bound; culture unmeasured | Prevention stays reactive; culture invisible | Register (federal-code model); KRIs; annual pulse | Medium |

5. Roadmap 2026–2028 (snapshot)

| Phase | Content | Headline KPI |
| --- | --- | --- |
| 1 · Foundation (Q4 2026 – Q2 2027) | Charter, mandate and manual approved; violations committee constituted (30-day decision standard); COI first cycle; gifts register; channel upgrade live; KPI page in ARCC pack; anti-retaliation monitoring defined | Whistleblowing score 2→4; independence Moderate-Low→Moderate-High |
| 2 · Enhancement (Q3 2027 – Q2 2028) | Case-management system; second and third certified investigators; risk-intelligence feeds (procurement, HR, finance) into standing KRIs; awareness attestation + culture pulse; ISO 37001 readiness | 100% of cases in system with SLA states; ≥10 standing KRIs |
| 3 · Intelligent Integrity (2028+) | NLP-assisted intake classification with mandatory human decision (UAE white space — no entity evidences AI triage of whistleblowing reports); ISO 37001→37301 certification; AI-fraud scenarios in the FRA cycle | First evidenced AI-assisted integrity intake in UAE government |

6. Top 10 Recommendations (full detail in Section 24 of the study)

| Recommendation | Benchmark | Priority | Timeline |
| --- | --- | --- | --- |
| 1 · Approve Integrity Office charter with investigation mandate | Mubadala | Critical | Q4 2026 |
| 2 · Upgrade reporting channel to the leading attribute set | ADNOC / FAB / Etihad | Critical | Live Q2 2027 |
| 3 · Constitute violations committee separated from investigation, 30-day decisions | DFSA / Dubai ECR 4/2019 | Critical | Q1 2027 |
| 4 · Codify the investigation manual from the operating method; train to it | Local white space | High | Q4 2026 |
| 5 · Launch annual COI declaration cycle + procurement COI gate | Etihad / Law 11/2023 | High | Q2 2027 |
| 6 · Implement case-management system encoding existing discipline | Composite | High | Q1 2028 |
| 7 · Stand up gifts register on the federal-code model | FAHR code | Medium | Q1 2027 |
| 8 · Channel and case KPIs in ARCC pack + post-report treatment monitoring | Emirates NBD / DFSA | Medium | Q1 2027 |
| 9 · Risk-intelligence feeds into standing KRIs for the FRA | FTA / Dubai FAA | Medium | Q2 2028 |
| 10 · ISO path (37001→37301, ISO 37002-conformant channel); then NLP-assisted intake, human decision | Mubadala / DEWA / TAMM precedent | Strategic | 2028 |

7. What This Means — and What We Do Not Know Yet

What this means: the path is conversion of an embodied practice into an institution — charter, committee, channel, system, programme, in that order; executed on this roadmap the profile moves from 57 to a defensible mid-70s, holding three artefacts no evidenced local government peer shows: a published investigation methodology, a measured integrity culture, and AI-assisted intake under human decision.

What we do not know yet: benchmark scores measure disclosed maturity only; every external claim is search-verified official content pending one-click URL confirmation (the environment blocked direct page fetching); the section’s staffing, budget and any internal policies outside the project record; whether Department-level gifts or COI machinery exists outside the record; the Penal Code self-reporting article number (secondary sources conflict — deliberately uncited).